## milestones+demos
Date | Person | Milestone | Demo
2017-04-23 | Sandy + Shariqah | Accurately track the IMU movement when the IMU is at an angle (because that is how it will be mounted to the pen). Have movements correspond to displacement in X, Y, Z | Use the serial monitor to continuously show our calculated displacement in the X, Y, Z,
| Violetta | Design the database that will be used for voice-to-speech commands, this will be a database that we only retrieve information from. Implement speech-to-text in code. It should include common phrases we expect the person to say. Start database that will keep track of pens current properties (color, size, etc.) | Speak a command into microphone and have the serial monitor show the corresponding properties that will change in response to this command. This command should be posted to an online database as well, which we can get the most recent values from.
| Yodahe | Research javascript API that can help us render 3D objects on a webpage. Figure out how to build simple functions using it. Possibly start writing a framework for classes that we can use (ex. a pen class that will have properties, and classes for the objects we draw so that we can keep track of instances). | Proof of concept: show that given expected data from our pen (x positions and y positions) we can draw 3D shapes by giving dummy values and displaying results on screen. Show whether the api library is able to handle continuous drawing or whether we will be implementing point to point.
April 30th | Violetta | Framework Building: Organize the current working files so that the ESP can access all functionality from one upload. Meaning, integrate the current speech-to-text into a main state machine based on the schematics that we drew up in the proposal. Make it easy for movement tracking to be implemented when done by including placeholder functions that will be defined later. | Run speech-to-text on the new framework and show that it still works in the defined state machine. If
| Yodahe | Concept Test: Test the lag between posting points online from the ESP to it being generated on the website. | Show timestamps that give the time from when the data (dummy point values) was posted to when it was rendered on the web page.
| Yodahe | Framework building: Make it such that the website is able to access the command database and make changes to the drawing pen for the next time that the person starts drawing. | Show this functionality working by changing the color of the pen using a speech command on the ESP or Postman POST (because it should be equivalent). We will not be writing any other commands because the work will be repetitive, so we will do that later.
| Everyone | Final attempt at using IMU motion to draw. We will each be attempting to implement a method of tracking some kind of motion. The main idea right now is to track initial "pushes" or "nudges" in directions which will then guide the drawing position in that direction until the user nudges in a new direction or stops drawing (releases button). We are also considering tilting or rotating to control motion. | Show our best attempt and the results of its calculated movements. If the results are good enough we will show the tracked position on the website. Otherwise, we will do something similar to the last checkoff where we focus on one direction and show what the current outputs are for our new method. If things look very dire, we will propose our new solution.
2019-05-07 | Everyone | Everyone will be given a speech command that is meant to give the pen more functionality. We plan on fully / successfully implementing at least three of the followings commands: change line color, change line weight, extrude an object along a line, drawing a box and sphere, ANYTHING ELSE? | Demonstrate that the spoken command makes the expected changes in the UI.
| SOMEONE? | Make a simple file with an already drawn / rendered outline of an object that users can practice drawing | Show the sample file and that it is possible to recreate it with our tool.
| Everyone | Design the final encasement for the P3N. Figure out where to find scrap materials and what shops on campus we will need access to. Right now our group has access to architecture shops and makerlodge shops. | Show the design and materials we plan on using, explain the building process that should be feasable to do within a week.
| Everyone | Start the documentation website for the project | Show plans or progress for website that presents our project.
2019-05-14 | Everyone | (test + debug) x 100 | Explain bugs that came up and how we fixed them.
| Everyone | Build the encasements for our products that we designed last week | Show off our manufacturing skills.
| Yodahe + Violetta | Final touches to UI of our pen | Show final UI
| Sandy + Shariqah | Finish project website page | Show final website for project
Note: Sorry these last few were very short descriptions, these will mostly be design choices that we make as we go along. The last week is also hopefully a buffer week for anything that goes wrong.